## Sheet1
A2B.js Task list
Feature | Story | Task | Started | Completed | Status
Play level | Main game loop |  | 2012-10-01 | 2012-12-01 | Done
Play level | Move ball |  | 2012-10-01 | 2012-12-01 | Done
Play level | If ball reaches end level complete |  | 2012-10-01 | 2012-12-01 | Done
Play level | If ball falls off level player dies | Monitor ball height (y coord) | 2013-02-15 | 2013-02-15 | Done
Play level | If ball falls off level player dies | Check if ball falls below a specific height | 2013-02-15 | 2013-02-15 | Done
Play level | If time runs out player dies | Display level time | 2013-02-15 | 2013-02-15 | Done
Play level | If time runs out player dies | Get time limit from level data | 2013-02-15 | 2013-02-15 | Done
Play level | If time runs out player dies | If time runs out player dies | 2013-02-15 | 2013-02-15 | Done
Play level | Select ball to play | Highlight selected ball
Play level | Select ball to play | Move selected ball
Play level | Select ball to play | Selected a different ball
Play level | Load level from file | Init three.js objects | 2012-10-01 | 2012-12-01 | Done
Play level | Load level from file | Init camera position at start of level | 2013-01-02 | 2013-01-02 | Done
Play level | Start level animation
Play level | End of level animation
Play level | Player dies animation
Play level | Start game animation
Play level | End game animation
Play level | If enemy hits ball player dies
Play level | If bonus collected score increased
Play level | Move animated blocks
Play level | Display level instructions |  | 2012-11-01 | 2012-11-01 | Done
Play level | Display high score table
Play level | Display score & time on HUD |  | 2013-01-07 | 2013-02-14 | Done
Play level | Load high scores
Play level | Enter name on high score table
Play level | Save high scores
Play level | If player hits switch animation starts/stops
Play level | If player hits switch light on/off
Edit level | Load level from file
Edit level | Save level to file
Edit level | Add block
Edit level | Edit block properties
Edit level | Delete block
Edit level | Add ball
Edit level | Edit ball properties
Edit level | Delete ball
Edit level | Add texture
Edit level | Edit texture properties
Edit level | Delete texture
Edit level | Add floor
Edit level | Edit floor properties
Edit level | Delete floor
Edit level | Add light
Edit level | Edit light properties
Edit level | Delete light
Edit level | Add wall
Edit level | Edit wall properties
Edit level | Delete wall properties
Level designs | Level 1 - basic forwards movement |  | 2013-01-02 | 2013-01-02 | Done
Level designs | Level 2 - left and right moves |  | 2013-01-03 | 2013-01-04 | Done
Level designs | Level 3 - up down left & right moves |  | 2013-01-04 | 2013-01-04 | Done
Level designs | Level 4 - rotate view to complete level |  | 2013-01-07 | 2013-01-07 | Done
Level designs | Level 5 - can run out of time |  | 2013-02-15 | 2013-02-15 | Done
Level designs | Level 6 - can fall off level and die |  | 2013-02-15 | 2013-02-15 | Done
Level designs | Level 7 - moving blocks
Level designs | Level 8 - moving enemy
Level designs | Level 9 - moving enemy & blocks
Level designs | Level 10 - level contains trigger switch to start movement
Level designs | Level 11 - level contains trigger switch to enable light
Level designs | Level 12 - multiple balls on level
Bugs
Play Level | Weird square shadow on top of block on level 4 | Amended shadow parms on camera in level4.json | 2013-01-07 | 2013-01-07 | Done
Play Level | camera rotation didn't feel natural | moved lookat position to origin | 2013-02-14 | 2013-02-14 | Done